## Project Charter
Group 3
Fashion Hub Store
Project Manager | Sipho Gcilishe
Project start date: | 2025-08-04 | Project end date: | 2025-08-22
E-Commerce Business Idea Concept
Fashion hub is a dynamic and modern online clothing and accessories destination, dedicated to delivering a curated selection of high-quality fashion for men , woman and children . Our platform has been designed to provide a seamless shopping experience , combining an easy-to-navigate interface with a wide range of styles that cater to diverse taste and preferences.We take pride in offering flexible and secure payment options, ensuring convenience and peace of mind for every customer. With fast and reliable delivery services, Fashion hub makes it possible for shoppers to enjoy their purchases quickly and hussle-free. Beyond just being a store, we also inspire our customers through our dedicated style inspiration section, helping them discover new trends and elevate their personal style. Our vision is to make premium and stylish fashion accessible to individuals across South Africa and beyond, bridging the gap between affordability and quality. At the heart of our mission lies a commitment to sustainability, as we actively support eco-friendly practices and partner with brands that share our dedication to ethical fashion.Through fashion hub we aim to redefine online shopping by merging convenience, style, and responsibility into one cohesive experience.
Fashion Hub Objectives |  |  |  | Benefits: Benefits to potential stakeholders by doing the project .
1.Our goal is to launch a fully functional and mobile-friendly e-commerce website by end August 2025, ensuring it is accessible and user-friendly for all customers. |  |  |  | 1. Wider market reach: local designers and suppliers will gain access to a much broader customer base, helping them grow their sales and establish stronger brand recognition
2. We aim to integrate secure online payment systems along with multi-currency support so that customers can shop conveniently and safely, no matter where they are. |  |  |  | 2. Customer Convenience: Stakeholders can capitalize on offering a seamless and accessible shopping experience to customers across the country,
3. We plan to build a catalog of at least 500 products , sourcing from both local and international brands to give customers variety and choice. |  |  |  | 3. Employment Creation: The project will open up new job opportunities in logistics, markeing and technology,contributing to economic growth and development.
4. Lastly , we want to implement a customer loyalty program designed to increase customer retention by at least 20% within the first year of operation. |  |  |  | 4. Stronger Brand Visibility: Through targeted digital marketing campaigns,stakeholders will benefit from increased brand awareness and stronger positioning in e-com space.
Stakeholder Requirements: |  |  |  | Project stakeholders:
Customers need a user friendly website with a wide variety of products , competitive pricing and dependable delivery services .Suppliers expect fair trade agreements , timely payments and opportunities to grow their brand visibility.Investors require regular performance reports , clear return-on-investment potential and solid growth strategies.Staff need proper training, open communication and a supportive work environment to perform effectively.Community expects ethical business practices , job creation and contributions to local economic growth.Partners look for collaboration opportunities , shared resources and mutual brand exposure.Regulatotors require compliance with industry laws, tax regulations and consumer standards. |  |  |  | The key stakeholders of the project include Project manager Sipho Gcilishe , the Design and development team Atang Makara , Laila Abduraham, Ay-yoob Dawood ,Mogamet Zuhayr Smith and Marketing Lead Laila Abduraham. Suppliers consist of local designers and import partners while investors are represented by the SA Angel Fund. The primary customers targeted are online shoppers across South Africa and neighboring countries. The project draws inspiration from successful brands such as Mr Price, The Fix and other leading clothing retailers , whose models of affordability , style and accessibility have shaped the vision for fashion hub .
Deliverables: List the core requirements of your e-commerce website. This includes functional and non-functional requirements.
F: User registration and login system with secure authentication |  | F: Integration with secure payment gateways (credit/debit cards or mobile) |  | NF: SEO-friendly architecture | NF: Social media integration
F: Product catalog with search ,filter and sorting options |  | F: Order tracking and delivery status updates |  | NF: Scalable infrastructure to handle growing traffic
F: Shopping cart and checkout process |  | F: contact forms and customers support |  | NF: high availability and uptime
Roles and responsibilities:
Name | Surname | Student number | Role | Cellphone | Email
Sipho | Gcilishe | N/A | Project manager & Frontend Developer | 069-258-8764 | siphogcilishe91@gmail.com
Laila | Abdurahman | N/A | frontend developer | 074-965-5878 | lailaabdurahman2206@gmail.com
Mogamet | Smith | N/A | Frontend & Backend developer | 082-665-5947 | mogametsmith34@gmail.com
Atang | Makara | N/A | frontend developer | 076-984-4768 | atangmakara16@gmail.com
Ay-yoob | Dawood | N/A | Frontend & Backend developer | 068-765-8890 | ay-yoobdawood72@gmail.com
Scope: |  |  |  | Out of Scope:
Fully functional e-commerce website with catalog , checkout , payment and loyalty system. Mobile -optimized responsive design. Integrated with payment gateways and order tracking . |  |  |  | AI-powered style recommendations for users , Advanced analytics dashboards with predictive sales trends . Multi-laguage support , AR/VR try-on feature for clothing and personalied email and SMS for notifications for promotions
Risks: |  |  | Constraints: |  | Mitigation:
Delay in supplier product delivery affecting catalog completion, Security vulnerabilities and potential data breaches , technical issues during website lauch, budget overruns due to unforeseen development costs and low user adoption or engagement. |  |  | Fixed project timeline(04 August 2025 - 22 August 2025), limited development and marketing budget and resource availability (development team and content creators ). |  | Maintain buffer periods in the project timeline, regular security audits and testing , prioritize critical features for launch , postpone non-essential featues, continuous communication with suppliers and stakeholders and early user testing and feedback loops to ensure adoption.
Assumptions: Known factors about the project that are not flexible.
Suppliers will provide accurate product information on time , internet infrastructure supports reliable website performance, customers have access to online payment methods , regulatory compliance will remain stable during the project period.
Comments/Notes:
The project aims to balance speed of lauch with quality and usability ,ongoing monitoring and improvements post-launch are planned and any additional features will be prioritized based on user feedback and available resources.